# Project Cost Granularity

Guardrails, and mandatory requirements

Purpose Define the mandatory, solution-neutral requirements needed to retain project execution cost granularity while keeping purchase order creation and approval simple, proportionate and operationally viable for Suppliers, Project Managers, Quality Managers and other approvers.

| Reference | P&A-REQ-001 |
| --- | --- |
| Version | 0.1 |
| Date | 21 September 2026 |
| Status | Draft requirements baseline |
| Scope | SAP S/4HANA, COUPA, Primavera P6, FastDraft |

# 1. Executive summary

The central design challenge is to preserve the granularity needed to attribute cost to an asset intervention, activity type and planned regulatory investment, without creating excessive purchase order lines, approval steps, duplicate data entry or manual reconciliation.

Overarching requirement The solution shall provide the required cost granularity and regulatory traceability without requiring equivalent granularity in every purchase order line or approval decision. It shall separate commercial approval grain, financial posting grain and analytical reporting grain, connecting them through controlled supplier detail, persistent identifiers, automated enrichment, deterministic attribution and governed allocation.

# 2. Solution guardrails

### G1. Capture once, reuse many times

Information shall be entered at the point where it naturally arises and reused or inherited downstream. Users shall not re-key data already held in an authoritative system or approved supplier submission. The authorized systems are:

- SAP S/4 for the financial data (actuals and Forecast)

- COUPA for Procurement data

- FastDraft for NEC compliance process and approvals.

- Primavera P6 for large Programme schedule and delivery

### G2. Separate the three grains

Commercial approval grain, financial posting grain and analytical reporting grain may differ. Their relationships must be explicit, controlled and auditable.

### G3. Simple approvals, accessible detail

Approvers shall see the scope, value, progress, quality status, forecast effect and material exceptions needed for their decision. Detailed coding shall be available by drill-down, not imposed as line-by-line approval effort.

### G4. No artificial PO-line proliferation

A purchase order shall not require a separate line for every activity, intervention or regulatory category unless a genuine commercial, accounting or control need exists.

### G5. Exceptions receive attention

Routine compliant transactions should follow a streamlined route. Manual review shall focus on material changes, control failures, ambiguous mappings and reconciliation breaks.

### G6. Preserve evidence and history

Original transactions, supplier submissions, mapping versions, allocation rules, approvals and corrections must remain reproducible and auditable.

Traceability hierarchy Regulatory commitment / investment -> intervention -> project -> site -> WBS -> activity type -> procurement or labour transaction -> actual or forecast cost -> delivered output -> commissioned asset(s)

# 3. Business outcomes and ownership

Mandatory requirements establishing the end-to-end outcome and accountability.

| ID | Mandatory requirement | Acceptance evidence |
| --- | --- | --- |
| BR-001 | Provide end-to-end traceability from each in-scope regulatory investment or commitment to the projects, interventions, activities, costs, outputs and supporting evidence through which it is delivered. | Sampled investment traces to source transactions and delivered outputs without an uncontrolled break. |
| BR-002 | Attribute project-execution cost to a project, WBS element, site or location, activity type and asset intervention at the agreed reporting grain. | Each in-scope cost contains or is associated by an approved rule with the required dimensions. |
| BR-003 | Link delivered cost and output information back to the planned investment submitted to the regulator. | Regulatory investment reference and applicable version are present in reporting lineage. |
| BR-004 | Preserve the relationship between original commitment, approved baseline, latest forecast, actual cost, estimate to complete and final outturn. | Controlled reports show each measure and variance using approved definitions and versions. |
| BR-005 | Avoid creating a second financial ledger outside the authoritative finance system. | Management and regulatory totals reconcile to authoritative financial actuals. |
| BR-006 | Support regional projects and Major Programmes through a common core model with controlled, approved variants. | Variants have documented applicability, justification, ownership and version. |

# 4. Processing efficiency and approval simplicity

Mandatory requirements that prevent reporting granularity from creating operational burden.

| ID | Mandatory requirement | Acceptance evidence |
| --- | --- | --- |
| EFF-001 | Maintain a simple and proportionate purchase order and approval process for Project Managers, Quality Managers and other operational approvers. | Representative users complete standard scenarios without unnecessary detail or navigation. |
| EFF-002 | Determine approval detail by the decision being made, not by the most granular downstream reporting requirement. | Approval views summarise decision-relevant information and provide optional drill-down. |
| EFF-003 | Do not require separate purchase order lines for every activity, intervention or regulatory category unless justified by a commercial, accounting or control need. | Design demonstrates analytical detail without artificial PO-line proliferation. |
| EFF-004 | Minimise duplicate entry of project, WBS, activity, site, intervention, contract and investment information across systems. | Authoritative values are reused or derived in representative scenarios. |

# 5. Granularity model

Requirements separating commercial approval, transaction and analytical grains.

| ID | Mandatory requirement | Acceptance evidence |
| --- | --- | --- |
| GRN-001 | Support different but connected levels of granularity for commercial approval, financial posting and analytical reporting. | Information model defines the relationship between all three grains. |
| GRN-002 | Allow a purchase order to be approved at an aggregated commercial level while its supporting supplier schedule contains granular activity, site or intervention detail. | Aggregated PO reconciles to its detailed schedule. |
| GRN-003 | Capture detailed supplier cost through FastDraft, APS or another controlled schedule where individual COUPA PO lines would be disproportionate. | Detailed records reconcile without equivalent PO-line creation. |
| GRN-004 | Maintain a persistent, version-controlled and auditable relationship between each aggregated PO line and supporting detailed cost schedule. | Detailed cost traces to PO, PO line, contract and financial posting. |
| GRN-005 | Ensure the supporting cost schedule does not become a separate financial ledger. | Analytical detail reconciles to SAP S/4 posted actuals. |
| GRN-006 | Avoid a PO amendment for redistribution of granular cost where total commitment, scope and approval thresholds are unchanged, subject to approved policy. | Controlled redistribution occurs without unnecessary reapproval. |
| GRN-007 | Trigger PO change or reapproval only for defined commercial, financial, scope, quality or control conditions. | Trigger conditions are approved and applied consistently. |
| GRN-008 | Provide approvers with summary and exception indicators, with drill-down to detail where required. | Users can make informed decisions without reviewing every allocation line. |
| GRN-009 | Distinguish supplier-declared detail, system-derived classification and governed allocation. | Each detailed record displays its origin and treatment. |
| GRN-010 | Ensure analytical classifications do not alter the legal or commercial meaning of the PO or contract unless formally incorporated. | Mappings remain separate from contractual terms unless approved. |

# 6. WBS and cost structure

Mandatory structure and posting requirements.

| ID | Mandatory requirement | Acceptance evidence |
| --- | --- | --- |
| WBS-001 | Carry persistent identifiers connecting WBS to investments, interventions, contracts, sites and schedules. | Cross-system matching works without free-text name matching. |
| WBS-002 | Control WBS creation and change, including validation of mandatory regulatory and intervention references. | Incomplete structures cannot be released without an approved exception. |
| WBS-003 | Preserve historic cost and lineage when WBS elements close, merge, split or restructure. | Historic outputs remain reproducible. |
| WBS-004 | Prevent or identify postings to unsuitable, closed or overly aggregated WBS elements. | Invalid postings are blocked or routed to a controlled exception. |

# 7. Activity taxonomy

Mandatory requirements for consistent activity-level analysis.

| ID | Mandatory requirement | Acceptance evidence |
| --- | --- | --- |
| ACT-001 | Establish a governed activity-type taxonomy for project-execution cost capture. | Approved code list has definitions, examples, owner and effective dates. |
| ACT-002 | Set activity granularity sufficient for regulatory evidence, forecasting, comparison and unit-cost analysis without disproportionate capture effort. | Representative scenarios demonstrate decision value and operability. |
| ACT-003 | Apply activity types consistently across supplier cost, internal labour, agency labour, materials and forecasts where relevant. | Equivalent work is classified consistently regardless of cost source. |
| ACT-004 | Map supplier-specific descriptions to controlled activity codes rather than creating uncontrolled enterprise codes. | Mappings are versioned and approved. |
| ACT-005 | Keep activity types distinct from WBS elements, interventions, cost elements and asset classes. | Glossary and model show separate concepts and relationships. |

# 8. Investment and intervention

Mandatory linkage and lifecycle requirements.

| ID | Mandatory requirement | Acceptance evidence |
| --- | --- | --- |
| INV-001 | Link each in-scope project to at least one valid planned investment, regulatory driver or approved non-regulatory funding source. | Projects without an approved link are reported as exceptions. |
| INV-002 | Assign persistent enterprise identifiers to investments and interventions. | Identifier continuity survives lifecycle change. |
| INV-003 | Support many-to-many relationships between investments, projects and interventions. | Split, aggregation and combined-delivery scenarios pass. |
| INV-004 | Record effective dates, status, source, owner and approval state for investment-to-project and project-to-intervention relationships. | Reports use the mapping valid for the selected period and version. |
| INV-005 | Preserve historic relationships through re-sanction, scope change, project split, intervention split and portfolio restructuring. | Historic regulatory outputs remain reproducible. |
| INV-006 | Distinguish regulatory intervention, asset under construction, finance asset and commissioned operational asset. | Each concept has separate definition, lifecycle and identifier. |
| INV-007 | Establish intervention relationships early enough to support execution forecasting and cost control. | Active projects can report actual and forecast by intervention. |
| INV-008 | On closure, enrich intervention records with delivered outputs and commissioned asset references where applicable. | One-to-many commissioning scenario is supported. |

# 9. Supplier and procurement detail

Mandatory supplier data and reconciliation requirements.

| ID | Mandatory requirement | Acceptance evidence |
| --- | --- | --- |
| SUP-001 | Define a common minimum supplier cost schema for all in-scope contract archetypes. | Schema identifies mandatory and conditional fields and validation rules. |
| SUP-002 | Include project, WBS, site, activity, cost category, period, quantity, unit, rate, amount, contract, PO and change references, plus intervention where known. | Representative supplier submission provides required data or approved exception. |
| SUP-003 | Define controlled submission routes for NEC, non-NEC, framework, direct-award, legacy and in-flight arrangements. | Every in-scope contract has an approved route. |
| SUP-004 | Validate detailed supplier cost before use in forecasting, attribution or regulatory reporting. | Validation covers schema, references, duplicates, arithmetic, period and relationships. |
| SUP-005 | Reconcile FastDraft or other supplier detail to contract, PO, receipt, invoice and financial posting where applicable. | Control totals and unresolved differences are visible. |
| SUP-006 | Prevent duplicate counting of supplier applications, invoices or cost lines. | Duplicate and superseded-version tests pass. |
| SUP-007 | Retain original submissions, corrections, approvals and superseded versions. | Auditor can identify the value used and its supporting evidence. |
| SUP-008 | Link compensation events, variations and scope changes to affected cost, activity, forecast and intervention records. | Change traces to financial effect and narrative evidence. |

# 10. Forecast, schedule and estimate to complete

Mandatory alignment between forecast and actual cost structures.

| ID | Mandatory requirement | Acceptance evidence |
| --- | --- | --- |
| FOR-001 | Use the same core project, WBS, intervention, activity and cost classifications for forecast and actuals at the agreed grain. | Comparison does not require uncontrolled remapping. |
| FOR-002 | Maintain approved baseline, current forecast, estimate to complete, commitments, actuals and final outturn as distinct measures. | Measures have approved definitions. |
| FOR-003 | Record as-at date, applicable period, version, status, preparer and approver for each forecast. | Reporting identifies the exact version used. |
| FOR-004 | Retain variance reason, scope or schedule driver and narrative for forecast changes. | Material movement is explainable and evidenced. |
| FOR-005 | Aggregate forecasts from execution detail to project, intervention, investment, portfolio and regulatory views. | All levels reconcile. |
| FOR-006 | Integrate supplier forecast information where suitable while covering non-NEC, internal and other costs. | Complete forecast is not dependent on one contract type. |
| FOR-008 | Validate missing periods, duplicates, stale forecasts, invalid mappings, unexpected movement and inconsistency with actuals or commitments. | Exceptions route to named owners. |
| FOR-009 | Control actualisation, roll-forward and restatement for closed periods. | Period-close scenario is repeatable and approved. |
| FOR-010 | Provide controlled forecast challenge and approval, not merely technical upload. | Evidence of review, challenge, approval and rejection exists. |

# 11. Applications and integration

Mandatory system responsibility, interface and reconciliation requirements.

| ID | Mandatory requirement | Acceptance evidence |
| --- | --- | --- |
| INT-001 | Retain SAP S/4 as authoritative for posted financial actuals unless explicitly changed by an approved architecture decision. | Regulatory totals reconcile to SAP S/4. |
| INT-002 | Ensure COUPA procurement transactions carry or inherit project and WBS references needed downstream. | Requisition-to-invoice tests retain required references. |
| INT-003 | Connect FastDraft detail to supplier, contract, PO, project, WBS and payment or invoice. | Application-for-payment scenario reconciles end to end. |
| INT-004 | Validate identifiers, codes, amounts, periods, currency, units, status and mandatory relationships at interfaces. | Invalid records are rejected or quarantined with reason. |
| INT-005 | Provide record and value control totals for sent, accepted, rejected and duplicate interface records. | Sending and receiving totals reconcile. |